## WBS
# | ACTIVITIES | ESTIMATE, h |  |  |  | ASSUMPTIONS
| FTEs: | min | max | Estimate, hours | Estimate, man-days
1 | Files: | 9 | 18 | 0 | 0
| Defining data types | 1 | 2 | 0 | 0
| Transformate data to general form | 8 | 16 | 0 | 0
2 | ETL: | 15 | 30 | 0 | 0
| Creating an ETL instance, or schema | 1 | 2 | 0 | 0
| Designing and developing a table for Avaya files | 2 | 4 | 0 | 0
| Design and development of a table for IPC files | 4 | 8 | 0 | 0
| Creating stored procedures for primary data processing | 8 | 16 | 0 | 0
3 | Cleaning | 16 | 32 | 0 | 0
| Creation of a cleaning instance, or scheme | 8 | 16 | 0 | 0
| Creating additional modifications | 8 | 16 | 0 | 0
4 | DWH | 40 | 80 | 0 | 0
| Creating a DWH | 10 | 20 | 0 | 0
| Tables for Avaya files for working with the DWH | 10 | 20 | 0 | 0
| Create a package for uploading data to the DWH | 10 | 20 | 0 | 0
| Create Staging | 8 | 16 | 0 | 0
| Create dimension | 2 | 4 | 0 | 0
5 | SSIS | 32 | 64 | 0 | 0
| Create a wizard for download packages | 8 | 16 | 0 | 0
| Create a Data Processing Package | 8 | 16 | 0 | 0
| Create a data cleaning package | 8 | 16 | 0 | 0
| Create a data download package | 8 | 16 | 0 | 0
6 | PowerBI | 8 | 16 | 0 | 0
| Create visualize the data through the Power BI | 8 | 16 | 0 | 0
7 | Log | 8 | 16 | 0 | 0
| Creating and developing a log table | 8 | 16 | 0 | 0
8 | Quality Control (50%) | 64 | 128 | 0 | 0
9 | Project Management Activities | 38.4 | 76.8 | 0 | 0
| TOTAL | 128 | 256

## Sheet1 (hidden)
| ACTIVITIES | BALLPARK ESTIMATE, HRS
| TOTAL | 10008
1 | Project Management | 1434
| Project Management and Coordination | 1290
| Requirements Management | 144
2 | Project Initiation | 248
| Project Environment | 168
| Development Environment | 48
| QA/Test Environment(s) | 80
| Staging Environment | 40
| Trainings and Knowledge Transfer | 80
3 | Infrastructure Management | 52
| Network Infrastructure | 8
| Define Project Network Security Policy | 4
| Network Security Implementation | 4
| Team Collaboration Environment | 32
| Branching Strategy Definition | 16
| SCM Usage Guide Preparation | 16
| Build and Integration Environment | 12
| Build infrastructure Definition | 12
4 | Design and Implemenation | 5260
| Swing part | 1256
| Embed Jasper reports viewer and create report runner | 32
| CRUD/browser for reports/templates/results | 120
| Criteria input form framework | 160
| Scheduler UI | 60
| Exporter UI | 32
| Add report permissions to existing ACL framework | 32
| Migrate to JIDE dashboard, create base classes | 80
| Create predefined real time reports |  | No inputs
| Reports customization UI | 120
| DB Maintenance UI | 32
| Report styling/logo UI | 40
| Export/import report UI | 40
| Embed existing JRubik functionality | 320
| See event details on analysis table | 80
| Executive report UI | 60
| Detailed report | 48
| Jasper part | 1104
| Create predefined report templates(33 basics, ~20 detailed, charts) | 528
| JRXML generation for customizable report | 320
| Chart and criteria naming practices | 16
| Create New Class Reports(assumption: 15 reports which have the similar complexity implementation as predefined report templates) | 240
| Server side java part | 1444
| Create report execution framework (both compiled and new) | 120
| SQL generation framework | 160
| ETL support from Java | 32
| Report CRUD/browser | 40
| Exporter/publisher | 60
| Enable Quartz and enable jobs scheduling | 32
| List scheduled jobs (both active and expired) and filter | 80
| Create jobs to execute report and publish it | 64
| Add report permissions to existing ACL framework | 32
| Filter data based on ACL | 80
| Filter reports based on ACL | 40
| Persist dashboard layout (widgets metadata need to be saved too) | 80
| Data providers for runtime reports | 80
| DB maintenance server side | 24
| Report migration | 80
| Report schedule migration | 80
| Report Result migration | 160
| Export/import template | 40
| Archive/restore | 40
| Save/execute executive report | 120
| ETL: Event and Dimentional Data Transfer | 496
| Changed Data Tracking | 24
| Control Flow Design: Data Extraction | 40
| Control Flow Design: SCD Type Dimentions Processing: (about 8 Dimentions) | 64
| Control Flow Design: Date/Time Dimention Processing | 24
| Control Flow Design: Geography Dimentions Processing | 40
| Control Flow Design: Fact Data Processing: (5 Fact Tables) | 80
| Control Flow Design: Aggregation Tables Preparation | 40
| Data Quality governance | 40
| Metadata Management | 40
| Configuration | 16
| Recovery and restart | 24
| Data Transformation Auditing | 24
| Logging | 24
| Scheduling approach | 16
| Data Warehouse (Vertica Database) | 336
| Star Schema Design (Review and Improve the previous Implementation) | 40
| Vertica Projections Design to have optimal reports execution | 40
| Fact Partitioning Strategy | 40
| Fact Aggregation Strategy | 40
| Large Dimension (Source and Destination IPs) | 24
| OLAP Cube Design(Review and Improve the previous Implementation) | 40
| Subdimension/Outriggers Design | 24
| Aggregate Navigator | 24
| Security: DB Layer | 32
| Security: OLAP Layer | 32
| Reports - BI part | 96
| Design Data Access Layer (Query Builder) | 80
| Create Queries for All Canned Reports(33 of them) | 16
| Dashboard - BI part | 120
| Prepare Additional DB Objects(Tables/Indexes) for Dashboards | 40
| Prepare Queries for Dashboard real time reports | 40
| Create process to populate preaggregated tables (Implemented as separate ETL Job) | 40
| Maintenance and Archiving - BI part | 96
| DW Purging: Automatic and OnDemand | 40
| DW Archiving and Restoring (Archive everything) | 8
| DW Archiving and Restoring (Archive part of history) | 24
| DW Archiving and Restoring (Archive dimention data) | 24
| Performance Optimization | 40
| Optimize the purging mechanism on WebNmsDB MySQL DB | 40
| Migration - BI part | 160
| Prepare Migration Scripts for Reports | 40
| Prepare Migration Scripts for Scheduling information | 40
| Prepare Migration Scripts for Report Results | 40
| ETL Part to Load Data from MySQL WebNmsDB for first time | 40
| Documentation - BI part | 112
| ETL Design | 24
| Source to target mapping | 24
| DW Design | 16
| OLAP model definition | 16
| System Decomposition and Deployment | 16
| Developer Guidelines for DW/ETL/Reports | 16
5 | Quality Assurance & Control | 2566
| Design QA Strategy | 16
| Design QA Strategy and Test Plan | 82
| QA Management and integration into Project team | 290
| Test Design Development | 750
| Requirements Analysis (Define Test Design Scope) | 240
| Design Test Design Framework | 4
| Design Test Cases/Scenarios/Functions | 456
| Web UI Testing | 40
| BI: Reports Content Testing | 26
| BI: Dashboard Testing | 30
| BI: Maintenance and Archiving | 8
| BI: Manual Performance testing of Data Warehouse (Report/Analysis Queries Benchmarking) | 26
| BI: Manual Performance testing of ETL (Event and Dimentional Data Transfer) | 26
| Functionality of Predefined Reports Testing | 80
| Functionality of Custom Reports Testing | 36
| Functionality of Analysis Reports Testing | 40
| Functionality of Shedules Testing | 40
| Functionality of Executive Reports Testing | 40
| Functionality of Dashboard Testing | 24
| Functionality of New Class Reports Testing | 24
| Migration Testing | 16
| Test Design Support | 50
| QA Construction | 1428
| Test Execution based on defined Testing Types | 1008
| Web UI Testing | 160
| BI: Reports Content Testing | 80
| BI: Dashboard Testing | 40
| BI: Maintenance and Archiving | 40
| BI: Manual Performance testing of Data Warehouse (Report/Analysis Queries Benchmarking) | 80
| BI: Manual Performance testing of ETL (Event and Dimentional Data Transfer) | 104
| Functionality of Predefined Reports Testing | 136
| Functionality of Custom Reports Testing | 56
| Functionality of Analysis Reports Testing | 56
| Functionality of Shedules Testing | 56
| Functionality of Executive Reports Testing | 56
| Functionality of Dashboard Testing | 32
| Functionality of New Class Reports Testing | 32
| Migration Testing | 80
| Regression Testing | 240
| Reporting Results | 60
| Defect Management | 120
Impact Analysis
6 | Deployment | 448
| Deployment Solution | 64
| Configure and run server side VM Image | 40
| Deployment Testing | 24
| CM Documentation | 64
| Build and Deployment Runbook | 24
| In-line Help | 24
| Development Environment Configuration Runbook | 16
| On-going Activities | 320
| Regular Deployment to Staging Environment | 160
| Regular Deployments to QA/Test Environment(s) | 160

## Sheet3 (hidden)
| ACTIVITIES | BALLPARK ESTIMATE, HRS
| TOTAL | 10008
1 | Project Management | 1434
| Project Management and Coordination | 1290
| Requirements Management | 144
2 | Project Initiation | 248
| Project Environment | 168
| Trainings and Knowledge Transfer | 80
3 | Infrastructure Management | 52
| Network Infrastructure | 8
| Team Collaboration Environment | 32
| Build and Integration Environment | 12
4 | Design and Implemenation | 5260
| Swing part | 1256
| Jasper part | 1104
| Create predefined report templates(33 basics, ~20 detailed, charts) | 528
| JRXML generation for customizable report | 320
| Chart and criteria naming practices | 16
| Create New Class Reports(assumption: 15 reports which have the similar complexity implementation as predefined report templates) | 240
| Server side java part | 1444
| ETL: Event and Dimentional Data Transfer | 496
| Data Warehouse (Vertica Database) | 336
| Reports - BI part | 96
| Dashboard - BI part | 120
| Maintenance and Archiving - BI part | 96
| Performance Optimization | 40
| Optimize the purging mechanism on WebNmsDB MySQL DB | 40
| Migration - BI part | 160
| Documentation - BI part | 112
| ETL Design | 24
| Source to target mapping | 24
| DW Design | 16
| OLAP model definition | 16
| System Decomposition and Deployment | 16
| Developer Guidelines for DW/ETL/Reports | 16
5 | Quality Assurance & Control | 2566
| Design QA Strategy | 16
| Design QA Strategy and Test Plan | 82
| QA Management and integration into Project team | 290
| Test Design Development | 750
| Requirements Analysis (Define Test Design Scope) | 240
| Design Test Design Framework | 4
| Design Test Cases/Scenarios/Functions | 456
| Test Design Support | 50
| QA Construction | 1428
| Test Execution based on defined Testing Types | 1008
| Regression Testing | 240
| Reporting Results | 60
| Defect Management | 120
Impact Analysis
6 | Deployment | 448
| Deployment Solution | 64
| CM Documentation | 64
| Build and Deployment Runbook | 24
| In-line Help | 24
| Development Environment Configuration Runbook | 16
| On-going Activities | 320